## Slide 1: Lessons learnt from MICE
K. Long
March 2, 2026

## Slide 7: Liquid-hydrogen system
Final cool-down start: 13Sep18
Fill start: 17Sep18
Absorber full: 25Sep18
Stable operation

## Slide 9: Evolution of Motivation 2003—2018

## Slide 10: Muon Collider and Neutrino Factory

## Slide 11: 2003/04: Astbury panel/proposal
No lower bound on q13
Indirect constraints on Higgs mass:
  LHC operations not yet started
  Energy frontier beyond LHC under discussion
Ionization cooling required:
  Neutrino Factory:
    Discovery reach to <~ 4 x 10-6
  Muon Collider:
    Luminosity to deliver multi-TeV collisions

## Slide 12: 2012: annus mirabilis
New Higgs-like state at 125 GeV:
  Clear programme @ LHC to test SM Higgs hypothesis
Daya Bay: q13 ~ 0.1 > 0:
  Conceivable to discover CP-invariance violation
  Neutrino Factory not required for next step in search for CP-invariance violation
ICHEP 2012: school-boy mean
[Risk noted in business case @ G/w 0]

## Slide 13: Projected sensitivity to CPiV
DUNE and Hyper-K alone:
  5σ sensitivity over >50% of all values of δCP after 10 yrs
Combined—sensitivity enhanced
LBNF/DUNE
J-PARC/Hyper-K

## Slide 14: 2018:
Looking beyond LHC @ DUNE/Hyper-K
EU Strategy update:
  Muon Collider w/g:
    Proton driven
    LEMMA; e+e- driven
MICE results important i/p to Strategy Update process
P5:
  Neutrino programme:
    LBNF/DUNE
    LBND
  Energy Frontier:
    LHC and its upgrades
    ILC

## Slide 15: A brief history
Collaboration perspective

## Slide 18: International review of MICE
Astbury Panel #1: 2002
Recommended full proposal be solicited
Among the recommendations:
Astbury Panel #2: 2003
Recommended approval of the proposal
Among the recommendations:

## Slide 19: Astbury #2, Gateway 0, 1, 2/3
It did not prove to be possible to deliver:
  RAL-based technical liaison in each critical sub-system; and
  RAL-owned Technical Advisory Committee
KL comment: would have been of substantial benefit
Joint (CCLRC/PPARC) MICE Project Board: 2003/05
  Oversaw MICE’s passage through Gateway Process:
    UK approval process for Government procurement (analogous to US Critical Decision process)
  Critical JMPB decisions:
    Staged implementation:
      Phase I: MICE to Step II
      Phase II: MICE to Step VI
    Air-cooled refrigerator to serve decay solenoid:
      PSI solenoid requires high-pressure He gas at 10K; final expansion is done in the magnet
      Consequence:
        Superconducting magnets for MICE cooled using cryocoolers
      Increased demands on design and execution of spectrometer, focusing and coupling magnets
KL comment:
  Reduced risk and cost to UK; arguably allowing project to be approved
  Increased risk and cost to collaborating institutes, in particular, the US

## Slide 20: CMPB 2005/10
CCLRC (later Collaboration) MICE Project Board
  Oversaw execution of Phase I project (to Step II); and
  Preparation of Phase II (MICE to Step VI)
Collaboration management of project:
  Through ‘Technical Coordinator’ (aka Project Manager); and
  Technical Board (http://mice.iit.edu/tb/)
Evolution of schedule:
  Delays in implementation of MICE Muon Beam
    Controlled by 2008, but, arguably focus on MMB issues meant that scrutiny of other aspects of MICE project by collaboration and CMPB was not so rigorous/detailed

## Slide 21: 2010—
MICE Project Board constituted 2010:
  Resource Loaded Schedule Review 2013—
Collaboration:
  MICE International Project Office: 2013—
Some key dates:
  Step I complete: 2010
  Stray field identified as an issue: Mar 2012
  SSU (SS2) delivered to RAL Aug 2013
  PRY adopted as solution: Sep 2013
  Focus-coil installed Oct 2013
  SSD (SS1) delivered to RAL Oct 2013
  SSU, SSD installed May, Jul 2014
  PRY complete May 2015
  Magnet commissioning start Jun 2015

## Slide 22: Rebaseling
US P5 review: May 2014
  Building for Discovery: Strategic Plan for U.S. Particle Physics in the Global Context
    “Realign activities in accelerator R&D with the P5 strategic plan. Redirect muon collider R&D and consult with international partners on the early termination of the MICE muon cooling R&D facility.”
MuPAC: July 2014
  From Office timeline summary:
    MICE seen as interesting benchmarking but not key to US programme
DOE MAP/MICE review: August 2014:
  Coupling coil removed from MICE cooling cell
MPB/RLSR: November 2014:
  Formal rebaseline:
    MICE programme will culminate in simplified cooling demonstration

## Slide 23: Turning points
13th September 2015:
  SSD M1 coil fails in training quench
26Oct15, 3/4Dec15: Magnet reviews (US/MAP):
  Replacement or refurbishment of SSD
MPB/RLSR: 03/04 April 2016:
  UK should seek to recover SSD with transfer of resource from US
STFC Cost to completion review: 26 April 2016:
  Rejects UK SSD recovery plan
  Recommends extended running in Step IV configuration and that collaboration be asked to submit a proposal for a cooling demonstration that could be performed with available equipment
MICE to STFC: May 2016:
STFC Executive Board: 26th May 2016:
  Rejects SSD recovery plan; rejects reconfiguration of cooling demonstration
  Approves extended operation of Step IV
Clearly a turning point: KL comments:
  Magnet training: over-extended many of the staff involved:
    Enhanced staffing essential for a future effort:
      Personnel to execute training
      Expert personnel: magnet, cryogenic and electrical to oversee and trouble-shoot
  Failure of M1 coil in SSD:
    Risk of such a failure could have been reduced:
      Stronger support at RAL by DL electrical experts and FNAL electrical/magnet/quench-protection experts
      Greater understanding of quench propagation in SS cold mass (2020 hindsight)
      Better record keeping and/or greater trained electrical/electronic technical support during QD/QP set up
      Enhanced QA/QC during magnet manufacture and possibly also intrinsic design issue(s)

## Slide 24: Observations
At the time the decision to cancel the cooling demonstration (with RF) was taken:
  The two single-cavity modules were at an advanced stage of preparation
    Prototype had delivered >20 MV/m and was ‘quiet’
  The RF amplifier had delivered 1 MW into a dummy load in DL
  New groups had joined the collaboration to contribute to the cooling demonstration:
    China: IHEP Beijing, Sichuan
    Korea: UNIST
    Serbia: Belgrade, Novi Sad

## Slide 25: Cost to completion
Asian and European:
  Began, formally, in 2005 (cost of proposal preparation earlier)
  Deliverables essentially on time, never on critical path
  Spend continues to present day

## Slide 26: Science and impact

## Slide 27: Publications

## Slide 28: Education and training
‘First destination returns’
Significant accelerator project experience:
  Lab and University;
  Early-career researcher and senior staff(!)

## Slide 29: Thoughts …

## Slide 30: Benefit of muon beams
Energy frontier: big advantage over pp because fundamental fermion
Future study of the Higgs:
  Line width; establish single resonance (?) in s-channel with m+m-
  Couplings; requires > 1 TeV for complete, precise study

## Slide 31: Lessons learnt …
… well … sound project management, etc. DOE labs good at this; so …
Consider, e.g., nuSTORM; development of FNAL muon complex for high-brightness beams …